## Goals Check
PRE-CONCEPTION GOALS CHECK
Started: 01.04.2021

focusing on improving the live of the user.	This being the first iteration, the goals do not apply
avoiding further destruction of Planet Earth.
being sustainable and unique
being secure and safe.
being free as in free speech
making a statement on what others can do.

## Conception
CONCEPTION PHASE
Started: 01.04.2021

Goal	Define a goal for my free time		Scope	Dependencies
Finished by	01.05.2021		Result is a document that will be included on every further project	My own free time
			Result → defines what I should do and what I shouldn’t do on my free time
			Result is a guideline to compare what I do against
			Result does not define what, it defines what for
REMEMBER:
	- Your Goal needs to be Specific, Measurable, Attainable, Relevant and Time Based / - “Finished by” does not have to necessarily be accurate yet. Modify it after Planning is ready. / - Scope is needed above all to define what your Goal is NOT. Bear that in mind throughout the whole project. / - Add as much as you can to both Scope and Dependencies, even if it’s obvious.

## Planning
	PLANNING PHASE
	Started: 01.04.2021					STATUS
						done
	REMEMBER:					working on it
		- Tasks need to be Specific, Measurable, Attainable, Relevant and Time Based / - One column for the “Task name”, another one for “Time to Finish” / - Any constraints to be taken into account can go into the “Time to Finish” / - Task 1a is a sub-task of Task 1 because it can only start after Task 1 is done / - Task 1 and Task 2 are independent from one another, therefore they go at the same level / - “Finish by:” must be after the biggest time to finish on that column / - Add each task and sub-task to a calendar of your preference to keep control of them

Finish by:	12.04.2021		14.04.2021		15.04.2021				-		-
	Brainstorming / of at least / 10 definitions	1 week
			Choose / a shortlist / and create / document	2 days / - 12-04 and 13.04 / Availability is short
					Review / Document	1 day

## Execution, Control
EXECUTION and CONTROL PHASE
Started: 02.04.2021

Task	Note
Brainstorming / of at least / 10 definitions	Need to take into account time available better

## Close
EXECUTION and CONTROL PHASE
Started: 11.04.2021
Finished: 11.04.2021
Note
It would be great to find techniques on defining the scope
Maybe we need to control the timing and calendar better, but that may complicate the document…we will try to create calendar entries instead